## Is Starbucks Your Cup of Coffee
Project 3 -- Is Starbucks Your Cup of Coffee?
Time in minutes | Anita | Asel | Harshita | Jeff | Ramya | Sneha | Total minutes | Total hours | Projected Time (mins) | Projected Time (hrs) | Delta
Exploration
1. Brainstorming - research and decide on the dataset | 36 | 36 | 36 |  | 36 | 36 | 180 | 3 | 120 | 2 | -1
2. Chart out the project roadmap and figure out what tools we are using |  | 20 |  |  |  |  | 20 | 0.33333 | 20 | 0.33333 | 0
3. Manpower Tracker |  | 20 |  |  |  |  | 20 | 0.33333 | 20 | 0.33333 | 0
4. Readme file |  | 40 |  |  |  |  | 40 | 0.66667 | 60 | 1 | 0.33333
Data Cleanup
2. Review the raw datasets |  | 15 |  |  |  |  | 15 | 0.25 | 20 | 0.33333 | 0.083333
3. Delegation of responsibilities: divide the 3 datasets | 5 | 5 | 5 |  | 5 | 5 | 25 | 0.41667 | 15 | 0.25 | -0.16667
4. Set objectives for each dataset | 10 | 10 | 10 |  | 10 | 10 | 50 | 0.83333 | 15 | 0.25 | -0.58333
[7 empty] | 0 | 0 |  |  | 0
Analysis
1. Decide on what method we are using and create the database/import data |  | 20 |  |  |  |  | 20 | 0.33333 | 40 | 0.66667 | 0.33333
2. Create a hypothesis |  | 5 |  |  |  |  | 5 | 0.083333 | 20 | 0.33333 | 0.25
3. Create custom tables, custom columns, charts |  | 120 |  |  |  |  | 120 | 2 | 160 | 2.6667 | 0.66667
[7 empty] | 0 | 0 |  |  | 0
Visualization
1. Pllotly |  | 250 |  |  |  |  | 250 | 4.1667 | 360 | 6 | 1.8333
2. Leaflet | [6 empty] | 0 | 0 | 120 | 2 | 2
3. HTML |  | 45 |  |  |  |  | 45 | 0.75 | 60 | 1 | 0.25
[7 empty] | 0 | 0 |  | 0 | 0
Github Collaboration
1. Create Github | [6 empty] | 0 | 0 |  | 0 | 0
2. Updating/merging/solving tech issues |  | 30 |  |  |  |  | 30 | 0.5 | 120 | 2 | 1.5
[7 empty] | 0 | 0 |  | 0 | 0
Merging and Data Cleanup
1. Clean the final code | [6 empty] | 0 | 0 | 45 | 0.75 | 0.75
2. Update the charts and decide the final version | [6 empty] | 0 | 0 | 25 | 0.41667 | 0.41667
[7 empty] | 0 | 0 |  | 0 | 0
Presentation
1. Design of PPT | [6 empty] | 0 | 0 | 75 | 1.25 | 1.25
2. Content for PPT | [6 empty] | 0 | 0 | 75 | 1.25 | 1.25
[7 empty] | 0 | 0 |  | 0 | 0
Total Time | 51 | 616 | 51 | 0 | 51 | 51 | 820 | 13.6667 | 1370 | 22.8333 | 9.1667 | 820
Team Members: Anita, Asel, Harshita, Ramya and Sneha
Dataset is available here. | [11 empty] | 16
960