## Is Starbucks Your Cup of Coffee
Project 3 -- Is Starbucks Your Cup of Coffee?
Time in minutes | Anita | Asel | Harshita | Jeff | Ramya | Sneha | Total minutes | Total hours | Projected Time (mins) | Projected Time (hrs) | Delta
Exploration
1. Brainstorming - research and decide on the dataset | 60 | 60 | 60 |  | 60 | 60 | 300 | 5 | 120 | 2 | -3
2. Chart out the project roadmap and figure out what tools we are using | 60 | 180 | 60 |  | 120 | 120 | 540 | 9 | 20 | 0.33333 | -8.6667
3. Manpower Tracker | 5 | 20 | 5 |  | 10 | 5 | 45 | 0.75 | 20 | 0.33333 | -0.41667
4. Readme file |  | 45 |  |  | 5 |  | 50 | 0.83333 | 60 | 1 | 0.16667
Data Cleanup
1. Review the raw datasets | 24 | 24 | 24 |  | 24 | 24 | 120 | 2 | 20 | 0.33333 | -1.6667
2. Delegation of responsibilities: divide the 3 datasets | 5 | 5 | 5 |  | 5 | 5 | 25 | 0.41667 | 15 | 0.25 | -0.16667
3. Set objectives for each dataset | 10 | 10 | 10 |  | 10 | 10 | 50 | 0.83333 | 15 | 0.25 | -0.58333
0
Analysis
1. Decide on what method we are using and create the database/import data | 320 | 200 | 60 |  | 120 | 210 | 910 | 15.1667 | 40 | 0.66667 | -14.5
2. Create a hypothesis | 60 | 5 | 15 |  | 30 | 15 | 125 | 2.0833 | 20 | 0.33333 | -1.75
0
Visualization
1. Pllotly | 180 |  | 90 |  | 120 | 90 | 480 | 8 | 360 | 6 | -2
2. HTML | 30 | 80 | 25 |  | 60 | 300 | 400 | 6.6667 | 60 | 1 | -5.6667
4. D3 JS |  | 400 |  |  |  |  | 400 | 6.6667 | 60 | 1 | -5.6667
5. Python, Pandas (cleaning Data) | 180 | 180 | 30 |  | 60 | 60 | 510 | 8.5 | 60 | 1 | -7.5
[10 empty] | 0 | 0
Github Collaboration
1. Create Github | [5 empty] | 15 | 15 | 0.25 |  | 0 | -0.25
2. Updating/merging/solving tech issues | 20 | 20 | 30 |  | 20 | 200 | 290 | 4.8333 | 120 | 2 | -2.8333
[10 empty] | 0 | 0
Merging and Data Cleanup
1. Clean the final code | 30 | 20 | 20 |  | 10 | 30 | 110 | 1.8333 | 45 | 0.75 | -1.0833
2. Update the charts and decide the final version | 30 | 45 | 60 |  | 30 | 15 | 180 | 3 | 25 | 0.41667 | -2.5833
[8 empty] | 0 |  | 0 | 0
Presentation
1. Design of PPT |  | 30 |  |  |  |  | 30 | 0.5 | 75 | 1.25 | 0.75
2. Content for PPT | 60 | 60 | 60 |  | 60 | 60 | 300 | 5 | 75 | 1.25 | -3.75
[10 empty] | 0 | 0
Total Time | 1074 | 1384 | 554 | 0 | 744 | 1219 | 4880 | 81.3333 | 1210 | 20.1667 | -61.1667
Team Members: Anita, Asel, Harshita, Ramya and Sneha
Dataset is available here.
Hours
Total Time Spent: | 81.3333